## Sheet1
Item and Assumptions | Assumptions | Consequence | Probability | Significance (P*C)
(4.15) Mgmt Review Incomplete | forgot one section | 30 | 5 | 150
(5.10) Cert Error | not measurement or uncertainty | 30 | 95 | 2850
(5.2) Staff Retiring < 2 year | unable to hire and crosstrain | 90 | 95 | 8550
(5.3) HVAC Out | funds and service available | 40 | 50 | 2000
(5.3) Lab Floods | only 3 floods in state labs in last 30 years | 95 | 5 | 475
(5.9) Failed PT | didn't get calibrations done | 90 | 15 | 1350
---
---
---
---
---
---
---
Example Rating Factors
Probability | Description
< 10 % | Remote
10 % to 35 % | Highly Unlikely
36 % to 50 % | Possible
51 % to 60 % | Probable
61 % to 90 % | Highly Likely
> 90 % | Certain
Consequence/Impact
< 10 | Insignificant; easily handled in the normal course of operations with no additional costs
10 to 25 | Minor; some disruption within normal functions and minimum estimated costs
26 to 50 | Moderate; immediate time/resource reallocations with moderate costs
51 to 75 | Major; operations severely disrupted and failure to part of operations is possible
> 76 | Critical; signficant concerns with ability to maintain operations
Significance | Prioritize by Sorting
Accept
Mitigate/Control
Transfer/Major Actions