HFP Teleconference

Friday, March 3, 2006

Attendee's:  Allan Eustis, John Wack, Sharon Laskowski, David Flater,

Whitney Quesenbery, Sharon Turner-Buie, Alice Miller,

John Cugini, Alexia Scott Morrison, Wendy Havens

Meeting begins: 11:30

Agenda:

* Briefly discussed items for the March  29th  plenary meeting; materials from

HFP, CRT & STS are out on the web; deadline for updates are

March 17th.

1)  TGDC and EAC updates, timeline / milestones, guidance and

equipment standards.

Updates about EAC meeting members attended; Donetta Davidson

would like to take part in some of the HFP  phone calls; timeline on drafts for

VVPAT-July '06, IV-Jan '07.

NVLAP will start pre-assessment visits to test labs; two will be done in April,

one in May; pre-assessment should identify needs required.

Useful to hear D. Davidson's election management guidance; idea

about usability issues discussed; doing a usability study, using bar codes,

getting data and where the barriers are.

2)  Comments on the  draft HFP documents.

Usability test; focus on two documents; specific areas to be clarified/

understood; testing to produce "pass/fail", "yes/no" data; ballot style; data

analysis; broken down by gender; user friendly applications.

Age level brought up…indicating more problems in the older voter

vs. the younger more "computer savvy" individual.

Need to have "real" test in order to expose true errors; pilot test might

be May or June.

3)  Addressing usability research, counting and VVPAT.

Plain language is well written document; EAC attention to issues very

important; discuss the possibility of holding test document; ballot design needs

more work on the guidance; navigation of ballot. Consensus is to hold document

out of March meeting.

Sharon Laskowski's meeting with Ginny Redish was useful; what next

document should look like.

Next HFP meeting is Friday, March 10, 2006 @ 2:30